## Sheet1
POLICY COMPLIANCE GAP ANALYSIS
Control Domain | Current State | Framework Requirement | Gap Identified | Risk Level | Owner | Remediation Plan | Target Date | Status | Evidence / Notes
Password Policy | Only length enforced | SOC 2 / ISO 27001 require complexity & rotation | Missing complexity & expiration rules | Medium | IT Security | Update policy & enforce system settings for complexity & reset | Q4 2025 | In progress | AD password policy screenshot
Data Backup | Daily backups, not tested | SOC 2 requires tested recovery | No restoration test done | High | IT Ops | Schedule quarterly recovery drill | Q3 2025 | In progress | Backup logs
Access Control | Broad user permissions | ISO 27001 requires least privilege / RBAC | No role-based access structure | Low | IT Manager | Implement RBAC & quarterly reviews | Q4 2025 | Open | Access control list
Incident Response | Plan exists, never tested | SOC 2 requires tested IR plans | No exercises done | Medium | SecOps | Conduct tabletop drill & document lessons learned | Q3 2025 | Closed | IR plan document
Vendor Risk Management | No vendor reviews done | SOC 2 requires vendor due diligence | No vendor assessments | Medium | Compliance | Create vendor risk questionnaire & review process | Q4 2025 | In progress | Vendor contracts
Data Encryption | Encrypted in transit only | SOC 2 & ISO require at-rest + transit | No encryption at rest | High | IT Security | Enable DB & storage encryption | Q4 2025 | Open | DB config evidence
Change Management | Ad hoc IT changes | ISO 27001 requires formal approval process | No documented change controls | Low | IT Ops | Establish change approval workflow | Q1 2026 | Open | Change request logs
Security Awareness | Training at onboarding only | SOC 2 requires annual refreshers | No recurring training | Medium | HR / Compliance | Launch yearly training & phishing tests | Q4 2025 | In Progress | Training records
Physical Security | Locked doors only | ISO 27001 requires facility monitoring | No visitor logs / CCTV | Medium | Admin | Implement visitor log + surveillance cameras | Q2 2026 | Open | Visitor log book
Data Retention | Data kept indefinitely | ISO 27001 requires retention schedules | No purge process | High | Compliance | Create retention policy & automate purging | Q4 2025 | In Progress | Policy draft
[10 empty] | Risk Level | Count | Percentage
[10 empty] | Low | 2 | 20% | 80%
[10 empty] | Medium | 5 | 50% | 50%
[10 empty] | High | 3 | 30% | 70%
[10 empty] | TOTAL | 10 | 100%
Status
Open
In progress
Closed
HIGH
MEDIUM
LOW
30%
50%
20%
RISK LEVEL OVERVIEW